## Frontend Sprint (Sep 4-10)
MeraBetta — Frontend Team — Weekly Sprint (Sep 4–10, 2026)
Day | Task Description | Assigned To | Status | Dependencies | Notes
Day 1 (Sep 4)
Day 1 (Sep 4) | Design & build Vendor Enrollment Form UI — all Nassery fields (Name, Address, Contact, License No, Capacity, Services, Photos upload, Documents upload) | Swaraj | Done | None | Multi-step form with ProgressBar, Section1OrgInfo, Section2FacilityDetails, Section3Documents, Section4CommercialTerms; Responsive design
Day 1 (Sep 4) | Implement client-side form validation (required fields, email format, phone format, file size limits), make the form multilingual (EN / HI / MR) | Swaraj | Done | FE-001 | Inline error messages; LanguageContext + translations.ts with 3 languages
Day 1 (Sep 4) | Set up API service layer — Axios/Fetch wrapper for enrollment form submission endpoint | Swaraj | Done | None | enrollmentApi.ts — Base URL config, error interceptor, auth token header
Day 2 (Sep 5)
Day 2 (Sep 5) | Build Admin Panel — Registration List View (table with search, filter by status, pagination, sort by date, export to Excel) | Swaraj | Done | FE-003 | admin/page.tsx — Columns: S.No, Name, Contact, Submitted Date, Status, Actions; session cache for records
Day 2 (Sep 5) | Build Admin Panel — Registration Detail View (full Nassery data, PDF document viewer, photo lightbox gallery, video player, approve/reject buttons) | Swaraj | Done | FE-004 | admin/enrollments/[id]/page.tsx — 1342 lines; real A4 PDF viewer, original PDF attachment, notes/reason field for rejection
Day 2 (Sep 5) | Integrate Enrollment Form with backend POST API — submit & show success/error feedback | Swaraj | Done | FE-001, BE-001 | MongoDB Atlas integration; Loading spinner, SuccessModal with form reset
Day 3 (Sep 6)
Day 3 (Sep 6) | Integrate Admin approval/reject actions with backend PATCH APIs + confirmation modal | Swaraj | Done | FE-005, BE-003 | Confirmation modal before approve/reject; updateRecordInCache for instant UI update
Day 3 (Sep 6) | Add Hospital at Home & Palliative/Bedridden care sections, Owner sign-off and digital signature to enrollment form | Swaraj | Done | FE-001 | Extended multi-step form with medical care fields and e-signature pad
Day 3 (Sep 6) | Implement vendor data migration transaction pipeline for legacy DB records | Swaraj | Done | BE-002 | vendorMigration.ts + testMigrationPipeline.ts; database seeds & audit logging
Day 4 (Sep 7)
Day 4 (Sep 7) | Build MeraBetta.com public-facing Senior Living Discovery Directory (/homes) — card/grid layout showing approved facilities with search, city filter, service type filter, capacity filter, price range filter, and sort options | Swaraj | Done | BE-005 | homes/page.tsx — FacilityCard component; debounced search; PublicNavbar + PublicFooter + FloatingWhatsApp
Day 4 (Sep 7) | Build MeraBetta.com Facility Detail Profile Page (/homes/[id]) — full vendor profile for public visitors with photo gallery, lightbox, services list, contact info, schedule visit modal | Swaraj | Done | FE-010 | homes/[id]/page.tsx — 43,653 bytes; PhotoLightbox, ScheduleVisitModal with form, responsive layout
Day 4 (Sep 7) | Build PublicNavbar, PublicFooter, FloatingWhatsApp components for the public-facing pages | Swaraj | Done | None | PublicNavbar.tsx, PublicFooter.tsx, FloatingWhatsApp.tsx — WhatsApp +91 93714 58326; mobile hamburger menu
Day 5 (Sep 8)
Day 5 (Sep 8) | Stabilize admin panel fetchEnrollments — fix re-render loop on View click, prevent DB reloads on back navigation using session caching | Swaraj | Done | FE-004 | adminCache.ts — generateQueryKey, getAdminQueryCache, setAdminQueryCache, clearAdminCache, checkAndConsumeBrowserReload
Day 5 (Sep 8) | Implement default sort to newest-first with robust multi-field timestamp sorting across admin records | Swaraj | Done | FE-004 | Sort by createdAt/submittedAt/updatedAt fallback chain; ArrowUpDown toggle
Day 5 (Sep 8) | Fallback to contact person details in admin panel when primary fields are missing; clarify seed record signatures for legacy data | Swaraj | Done | FE-005, BE-003 | Graceful null handling; consistent display for migrated records
Day 6 (Sep 9)
Day 6 (Sep 9) | Tailor /homes for direct end-users — remove vendor/admin navigation links, update WhatsApp number, polish UX for public visitors | Swaraj | Done | FE-010 | Removed admin header links; updated contact to +91 93714 58326
Day 6 (Sep 9) | Remove WhatsApp button from top navbar and keep it only on the floating widget for cleaner UI | Swaraj | Done | FE-010 | Cleaner navbar; FloatingWhatsApp as single entry point
Day 6 (Sep 9) | Add multi-language support (Hindi & Marathi) to public pages and update exact brand logo wordmark in navbar | Swaraj | Done | FE-001 to FE-015 | i18n LanguageContext + translations.ts — EN/HI/MR switcher; BrandLogo.tsx with exact wordmark
Day 7 (Sep 10)
Day 7 (Sep 10) | End-to-end integration testing — full flow: enrollment form → admin list → admin detail → approve/reject → public /homes listing → /homes/[id] detail | Swaraj | Not Started | All FE tasks | Document test cases & results; cover all 3 languages
Day 7 (Sep 10) | Bug fixes, code review, documentation, and deployment prep | Swaraj | Not Started | FE-019 | README, env config, build optimization, next.config.ts verification
✅ Completed: 18/20 tasks ¦ 🔴 Remaining: 2/20 tasks